## Sheet1
CSI4142 - Project 2023
Phase 3- OLAP and BI Dashboard
Teamwork - breakdown of duties
Deliverable checklist | Responsible | Expected completion date | Actual completion date | Estimated | Actual | Notes (if any)
| team member(s) |  |  | time (hours) to complete | time (hours) to complete
OLAP queries | Simon and Nicholas | 2023-04-11 | 2023-04-11 | 2 | 4
Drill down, roll up | Simon and Nicholas | 2023-04-11 | 2023-04-11 | 2 | 4
Slice | Simon and Nicholas | 2023-04-11 | 2023-04-11 | 2 | 4
Dice | Simon and Nicholas | 2023-04-11 | 2023-04-11 | 2 | 4
Composite OLAP - 4 queries | Simon and Nicholas | 2023-04-11 | 2023-04-11 | 2 | 4
Icebergs | Nicholas | 2023-04-11 | 2023-04-11 | 2 | 4
Windowing - partition | Nicholas | 2023-04-12 | 2023-04-12 | 2 | 4
Window | Nicholas | 2023-04-13 | 2023-04-13 | 2 | 4
|  | 2023-04-14 | 2023-04-14 | 2 | 4
BI dashboard | Sebastien | 2023-04-15 | 2023-04-15 | 2 | 4
Design of data mart | Nicholas | 2023-04-16 | 2023-04-16 | 2 | 4
Importing data | Sebastien | 2023-04-17 | 2023-04-17 | 2 | 4
OLAP queries | Nicholas | 2023-04-18 | 2023-04-18 | 2 | 4
Figures | Sebastien | 2023-04-19 | 2023-04-19 | 2 | 4
|  | 2023-04-20 | 2023-04-20 | 2 | 4
Other tasks - please specify |  | 2023-04-21 | 2023-04-21 | 2 | 4