## Phase3-TeamPlanning2023
CSI4142 - Project 2023
Phase 4 - Data Mining
Teamwork - breakdown of duties
Deliverable checklist | Responsible | Expected completion date | Actual completion date | Estimated | Actual | Notes (if any)
| team member(s) |  |  | time (hours) to complete | time (hours) to complete
Data preprocessing | Nicholas | 2023-04-09 | 2023-04-11 | 2 | 4
Data summarisation | Nicholas | 2023-04-09 | 2023-04-11 | 2 | 4
.. Visualisation of attributes | Nicholas | 2023-04-09 | 2023-04-11 | 2 | 4
Data transformation | Nicholas | 2023-04-09 | 2023-04-11 | 2 | 4
.. Missing values | Nicholas | 2023-04-09 | 2023-04-11 | 2 | 4
.. Categorical data | Nicholas | 2023-04-09 | 2023-04-11 | 2 | 4
.. Numeric data | Nicholas | 2023-04-09 | 2023-04-11 | 2 | 4
.. Feature selection | Nicholas | 2023-04-09 | 2023-04-11 | 2 | 4
Data mining - Classification | Simon and Sebastien | 2023-04-09 | 2023-04-11 | 2 | 4
Decision tree | Simon and Sebastien | 2023-04-09 | 2023-04-11 | 2 | 4
Gradient Boosting | Simon and Sebastien | 2023-04-09 | 2023-04-11 | 2 | 4
Random Forests | Simon and Sebastien | 2023-04-09 | 2023-04-11 | 2 | 4
Comparison of results | Simon and Sebastien | 2023-04-09 | 2023-04-11 | 2 | 4
Summary | Simon and Sebastien | 2023-04-09 | 2023-04-11 | 2 | 4
Anomaly detection | Simon and Sebastien | 2023-04-09 | 2023-04-11 | 2 | 4
One-class SVM | Simon and Sebastien | 2023-04-09 | 2023-04-11 | 2 | 4
Summary | Simon and Sebastien | 2023-04-09 | 2023-04-11 | 2 | 4
Other tasks - please specify